## Deliverables
UNIT |  | OBEO |  | AIRBUS |  | MANTIS |  | LORIA |  | KocSistem |  | HISBIM |  | SOGETI
SW | Doc | SW | Doc | SW | Doc | SW | Doc | SW | Doc | SW | Doc | SW | Doc | SW | Doc
D3.3.1-1 Transformation Manager component (release 1) (M10) | D5.1.1 Project Kick-Off Report and Project Management Plan (M1) | D6.1.1 Prototype Core ModelWriter (M7) | D7.1.1 Dissemination Plan (M6) | D1.3.2 Corpus for French Use Cases (Public) (M8) | D1.3.1 Industrial Use Cases for French Consortium (M8) | D1.4.3 Corpus for Turkish Use Cases (Private) (M8) | D1.4.1 Industrial Use Cases for Turkish Consortium (M8) | D2.5.2-1 Natural Language Generator and Documentation (release 1) (M16) | D2.3.1 Overview and comparison of existing generators (M8) | D6.3.1-1 Writer enhancements (release 1) (M10) | D4.2.1 Interface Control Document (ICD) (M9) |  | D1.5.1 Minutes of the User Requirements Review meeting (M8) | D1.2.3 Corpus for Belgian Use Cases (Private) (M13) | D1.2.1 Industrial Use Cases for Belgian Consortium (M13)
D3.4.1-1 Configuration Manager component (release 1) (M10) | D3.1.1 Review of model-to-model transformation approaches and technologies (M8) | D7.4.1 ModelWriter-ITEA website (M8) | D6.2.1 Architectural Design Document (ADD) (M8) | D1.3.3 Corpus for French Use Cases (Private) (M8) | D7.2.1-1 Exploitation and Marketing Plan (release 1) (M8) | D1.4.2 Corpus for Turkish Use Cases (Public) (M8) | D4.1.1 Knowledge Base Design document (M9) | D2.5.1-1 Semantic Parser and Documentation (release 1) (M18) | D2.1.1 Software Requirements - Evaluation of the NLP requirements set by the use cases (M10) | D6.5.2-1 Automated Acceptance Tests (release 1) (M12) | D1.6.2 Software Requirements Document (SRD) (M9) |  | D1.1.1 Evaluation Methods & Tools (M9) | D1.2.2 Corpus for Belgian Use Cases (Public) (M13)
D3.5.1-1 Traceability Manager component (release 1) (M10) | D1.5.2 User Requirements Document (URD) (M8) | D6.4.2-1 User Interface for the Writer part (release 1) (M12) | D6.4.1 Ergonomics Guidelines document for the Writer Part (M9) |  | D1.6.1 Minutes of the Software Requirements Review meeting (M9) | D4.3.1-1 Knowledge Base (release 1) (M13) | D4.5.1 Technical Note for KB serialization and reuse (M13) |  | D2.1.2 Corpora (Text, Knowledge, Bi-Texts) and Documentation (M12) |  | D6.5.1-1 Acceptance Test Plan (release 1) (M12)
D3.6.1-1 Synchronization Manager component (release 1) (M10) | D5.2.1 Project Progress Report (first half year) (M8) | D6.4.3-1 IDE-integrated User Interface to handle Sync issues (major release 1) (M12) | D1.8.1 Technical Risk Assessment Document (M9) |  | D1.7.1-1 Annual Product Owner Review - 1 (M17) |  | D4.7.1 Future ModelWriter-Enabled Use Cases (M14) |  | D2.4.1 Specification of the Knowledge Representation Language (M14) |  | D6.6.1-1 Acceptance Test Procedures (release 1) (M14)
D7.6.1 ModelWriter-ITEA's LinkedIn Group (M10) | D3.2.1 M2M Transformation Framework architectural design document (M8) | D4.6.2-1 Proof-of-concept semantic comparison engine (release 1) (M13) | D7.5.1 Technical-oriented talk about the principles and benefits of the ModelWriter-ITEA approach and tooling (M10) | [7 empty] | D6.8.1-1 Evaluation report (release 1) (M17)
D7.6.2 ModelWriter-ITEA's Twitter Group (M10) | D7.5.2 Research-oriented talk about the principles and benefits of the ModelWriter-ITEA approach and tooling (M10) | D6.7.1-1 ModelWriter major release (release 1) (M16)
D3.8.1-1 Source code of each m2m transformation (release 1) (M13) | D5.2.2 Project Progress Report (second half year) (M13) | D6.7.2-1 WP2 Integration in ModelWriter and Documentation (release 1) (M18)
Note on E3: Moharram Challenger: Ferhat will put the data in the private repo

## Presentations
WP # | WP Name | WP Leader | Presenter | Slides? | Commet
WP1 | Industrial Use Cases and Requirements | Airbus | Anne | √ | Need to report the progress
WP2 | Semantic Parsing Generation of Documents and Documents Components | Loria | Claire, Meriem | √ | GOOD!
WP3 | Model <==> Knowledge Base Synchronization | UNIT | Ferhat, Moharram
WP4 | Knowledge Base Design and Implementation | MANTIS | Erhan | √ | No details
WP5 | Project Management | UNIT | Ferhat
WP6 | Architecture, Integration and Evaluation | OBEO | Yvan | √
WP7 | Standardization, Dissemination and Exploitation | OBEO | Yvan | √
UC # | UC Name | UC Owner | Presenter | Slides?
UC-FR-01 | Synchronization between Models and Documentation | OBEO | Yvan | √ | No Demo
UC-FR-02 | Enterprise Architecture | OBEO | Yvan | √ | No Demo
UC-FR-03 | Synchronization of regulation documentation with a design rule repository | Airbus | Anne | √ | Demo ???
UC-FR-04 | Production of a context specific design document | Airbus | Anne | √ | Demo ???
UC-TR-01 | Documents of Quality Assurance Department | Hisbim | Ersan | √ | Title change, No demo, Need Change request
UC-TR-02 | Non-Disclosure Agreements | Hisbim | Ersan | √ |  | Non-Disclosure Agreements
UC-TR-03 | Synchronization of ReqIF/Clafer models with requirement specifications | UNIT | Ferhat |  | HAS Demo
UC-TR-04 | Integration with Application Lifecycle Management (ALM) Tools | Havelsan-UNIT | Eray | √ | Title change, Need Change request
UC-TR-05 | Synchronous Business Process Design with Use Cases | UNIT | Geylani |  | HAS Demo
Demo # | Demo Name | Demo Owner | Presenter | Related to… | Video?
Demo 1 | Semanitc parsing: Extracting and Checking | Loria | Meriem | WP2, UC-FR-03, UC-FR-04
Demo 2 | Writer part
Demo 3 | Model part
Demo 4 | Synchronization: Mapping and Linking |  |  | WP3, UC-TR-03, UC-TR-04
Demo 5
Demo 6
Demo 7
Demo 8
Important items
Market access (and market plan)
SotA and competitor tools
demonstrations,
exploitation strategy