ModelWriter

[WP1 - Industrial Use Cases and Requirements (AIRBUS) 3](#_Toc412552960)

[T1.1 - Evaluation Methods & Tools [UNIT + KOCSISTEM + AIRBUS + OBEO + HISBIM + MANTIS] 3](#_Toc412552961)

[T1.2 - Industrial Use Cases for Belgium Consortium [SA -> Sogeti] 3](#_Toc412552962)

[T1.3 - Industrial Use Cases for French Consortium [AIRBUS + OBEO] 4](#_Toc412552963)

[T1.4 - Industrial Use Cases for Turkish Consortium [MANTIS + UNIT + KOCSISTEM + HISBIM] 4](#_Toc412552964)

[T1.5 - Consolidated User Requirements [SA -> AIRBUS + OBEO + MANTIS ++ Sogeti] 4](#_Toc412552965)

[T1.6 - User Requirements Review [SA -> AIRBUS + UNIT + KOCSISTEM + KUL + ALL] 4](#_Toc412552966)

[T1.7 - Software Requirements [SA -> AIRBUS + LORIA + UNIT + MANTIS + OBEO] 5](#_Toc412552967)

[T1.8 - Software Requirements Review [SA -> AIRBUS + UNIT + KOCSISTEM + ALL] 5](#_Toc412552968)

[T1.9 - Annual Product Review [SA -> AIRBUS + Country Coordinators - "Product Review Committee"] 5](#_Toc412552969)

[T1.10 - Technical Risk Assessment and Management [OBEO + UNIT + KOCSISTEM + ALL] 5](#_Toc412552970)

[WP2 - Semantic Parsing and Generation of Documents and Documents Components (LORIA) 6](#_Toc412552971)

[T2.1 - Data Collection [LORIA + KUL -SA ++ OBEO ++ AIRBUS ++Sogeti] 6](#_Toc412552972)

[T2.2 - Hybrid approaches to semantic parsing [KUL1 + LORIA] 6](#_Toc412552973)

[T2.3 - Hybrid approaches to Natural Language Generation [LORIA - KUL2 + KUL1] 7](#_Toc412552974)

[T2.4 - Definition of the target semantic representation language [- KUL2 + KUL1 + LORIA ++ OBEO ++ AIRBUS] 7](#_Toc412552975)

[T2.5 - Development of the semantic parser and of the generator [LORIA + KUL1 + MANTIS - KUL2 + AIRBUS ++ OBEO] 7](#_Toc412552976)

[WP3 - Model to/from Knowledge Base (UNIT) 9](#_Toc412552977)

[T3.1 - Review of M2M transformation approaches [UNIT + KOCSISTEM] 9](#_Toc412552978)

[T3.2 - Specification and design of the M2M Transformation Framework [UNIT + KOCSISTEM] 9](#_Toc412552979)

[T3.3 - Development of the Transformation Manager component [UNIT + KOCSISTEM] 9](#_Toc412552980)

[T3.4 - Development of the Configuration Manager (COM) component [UNIT + KOCSISTEM] 10](#_Toc412552981)

[T3.5 - Development of the Traceability Manager component [UNIT + KOCSISTEM] 10](#_Toc412552982)

[T3.6 - Development of the Synchronization Manager component [UNIT + KOCSISTEM] 11](#_Toc412552983)

[T3.7 - Design of the model-to-model transformations [UNIT + MANTIS + KUL2] 11](#_Toc412552984)

[T3.8 - Implementation of the model-to-model transformations [UNIT + KUL2] 11](#_Toc412552985)

[T3.9 - Validation of the M2M Transformation Framework [UNIT + MANTIS + KUL2 + KOCSISTEM] 11](#_Toc412552986)

[WP4 - Knowledge Base Design and Implementation (Mantis) 13](#_Toc412552987)

[T4.1 - Design of the Knowledge Base [+ KUL2 - SA + OBEO + MANTIS + UNIT + KOCSISTEM] 13](#_Toc412552988)

[T4.2 - API of the Knowledge Base [+ KUL2 + KOCSISTEM + OBEO + UNIT] 13](#_Toc412552989)

[T4.3 - Implementation of the Knowledge Base [- KUL2] 13](#_Toc412552990)

[T4.4 - Plug-in #1: ModelWriter-assisted requirements review [- KUL2 - SA] 14](#_Toc412552991)

[T4.5 - Knowledge Base serialization and reuse plug-in [MANTIS] 14](#_Toc412552992)

[T4.6 - Plug-in #3: ModelWriter-assisted semantic comparison of 2 documents [OBEO + MANTIS] 14](#_Toc412552993)

[T4.7 - Plug-in #2: ModelWriter-assisted compliance review [-SA] 15](#_Toc412552994)

[T4.9 - Internal bi-directional synchronization mechanism [OBEO + UNIT] 15](#_Toc412552995)

[T4.10 - External synchronization mechanism for collaborating ModelWriters [SA] 15](#_Toc412552996)

[WP5 - Project Management (UNIT) 16](#_Toc412552997)

[T5.1 - Communication Management and Collaboration Infrastructure [UNIT + WP7 leader] 16](#_Toc412552998)

[T5.2 - Project Coordination and Reporting [UNIT - SA + Country Coordinators + WP Leaders] 16](#_Toc412552999)

[T5.3 - Closing Project [UNIT + WP Leaders] 17](#_Toc412553000)

[WP6 - ModelWriter Architecture, Integration and Evaluation (OBEO) 18](#_Toc412553001)

[T6.1 - Experimental Prototyping [OBEO - SA - KUL2] 18](#_Toc412553002)

[T6.2 - Architectural Design [OBEO - SA - KUL2 + MANTIS + UNIT + technological WP Leaders] 18](#_Toc412553003)

[T6.3 - Writer Part enhancements [- SA] 18](#_Toc412553004)

[T6.4 - User Interfaces Implementation [- SA + OBEO] 19](#_Toc412553005)

[T6.5 - Acceptance Test Plan [- SA + UNIT + KS + ALL] 19](#_Toc412553006)

[T6.6 - Acceptance Test Procedures [- SA + UNIT + KS + ALL] 20](#_Toc412553007)

[T6.7 - ModelWriter Integration [OBEO + UNIT + ALL] 20](#_Toc412553008)

[T6.8 - Cyclic Evaluation of Analysis Performance [- SA + OBEO + LORIA + UNIT + KS + ALL] 21](#_Toc412553009)

[WP7 - Dissemination and Exploitation (OBEO) 22](#_Toc412553010)

[T7.1 - Dissemination Plan [OBEO + UNIT + SA + LORIA + KS + ALL] 22](#_Toc412553011)

[T7.2 - Business Model & Exploitation Plan [AIRBUS + SA + OBEO + all industrial partners] 22](#_Toc412553012)

[T7.3 - Workshops & Events [+ KUL2 + UNIT + OBEO + KS + AIRBUS + ALL] 23](#_Toc412553013)



[T7.4 - ModelWriter-ITEA Consortium Website [- SA] 23](#_Toc412553014)

[T7.5 - Community Forum & Open Source Campaign [+ KUL2 + OBEO] 23](#_Toc412553015)

[T7.6 - Social Networks [UNIT + KOCSISTEM] 23](#_Toc412553016)

[T7.7 - Standardization [LORIA + UNIT + KOCSISTEM] 24](#_Toc412553017)

## WP1 - Industrial Use Cases and Requirements (AIRBUS)

### T1.1 - Evaluation Methods & Tools [UNIT + KOCSISTEM + AIRBUS + OBEO + HISBIM + MANTIS]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M5] | D1.1.1 Report: Evaluation Methods & Tools | Doc. | Public | UNIT -> HISBIM |

### T1.2 - Industrial Use Cases for Belgium Consortium [SA -> Sogeti]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M7] | D1.2.1 Report: Industrial Use Cases for Belgian Consortium | Doc. | Public | Sogeti |
| [M3 -> M7] | D1.2.2 Data: Corpus for D1.2.1 (public part) | SW | Public | Sogeti |
| [M3 -> M7] | D1.2.3 Data: Corpus for D1.2.1 (confidential part) | SW | Confidential | Sogeti |

### T1.3 - Industrial Use Cases for French Consortium [AIRBUS + OBEO]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M5] | D1.3.1 Report: Industrial Use Cases for French Consortium | Doc. | Public | AIRBUS |
| [M3 -> M5] | D1.3.2 Data: Corpus for D1.2.1 (public part) | SW | Public | AIRBUS |
| [M3 -> M5] | D1.3.3 Data: Corpus for D1.2.1 (confidential part) | SW | Confidential | AIRBUS |

### T1.4 - Industrial Use Cases for Turkish Consortium [MANTIS + UNIT + KOCSISTEM + HISBIM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M7] | D1.4.1 Report: Industrial Use Cases for Turkish Consortium | Doc. | Public | MANTIS |
| [M3 -> M7] | D1.4.2 Data: Corpus for D1.3.1 (public part) | SW | Public | MANTIS |
| [M3 -> M7] | D1.4.3 Data: Corpus for D1.3.1 (confidential part) | SW | Confidential | MANTIS |

### T1.5 - Consolidated User Requirements [SA -> AIRBUS + OBEO + MANTIS ++ Sogeti]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M7] | D1.5.1 Report: User Requirements Document (URD) for ModelWriter | Doc. | Public | SA -> UNIT |

### T1.6 - User Requirements Review [SA -> AIRBUS + UNIT + KOCSISTEM + KUL + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M7] | D1.6.1 Report: Minutes of the User Requirements Review meeting | Doc. | Public | SA -> AIRBUS -> HISBIM |

### T1.7 - Software Requirements [SA -> AIRBUS + LORIA + UNIT + MANTIS + OBEO]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M5 -> M9] | D1.7.1 Report: Software Requirements Document (SRD) for ModelWriter | Doc. | Public | SA -> KOCSISTEM |

### T1.8 - Software Requirements Review [SA -> AIRBUS + UNIT + KOCSISTEM + ALL]

| Month | Deliverable | Type | Access | Leader |
| --- | --- | --- | --- | --- |
| [M5 -> M9] | D1.8.1 Report: Minutes of the Software Requirements Review meeting | Doc. | Public | SA -> AIRBUS |



### T1.9 - Annual Product Review [SA -> AIRBUS + Country Coordinators - "Product Review Committee"]

| Month | Deliverable | Type | Access | Leader |
| --- | --- | --- | --- | --- |
| [M13 -> M15] | D1.9.1-1 Report: Annual Product Owner Review | Doc. | Public | SA -> AIRBUS |
| [M25 -> M26] | D1.9.1-2 Report: Annual Product Owner Review | Doc. | Public | SA -> AIRBUS |
| [M37] | D1.9.1-3 Report: Annual Product Owner Review | Doc. | Public | SA -> AIRBUS |

### T1.10 - Technical Risk Assessment and Management [OBEO + UNIT + KOCSISTEM + ALL]

| Month | Deliverable | Type | Access | Leader |
| --- | --- | --- | --- | --- |
| [M5 -> M9] | D1.10.1 Technical Risk Assessment Document | Doc. | Public | OBEO |

## WP2 - Semantic Parsing and Generation of Documents and Documents Components (LORIA)

### T2.1 - Data Collection [LORIA + KUL -SA ++ OBEO ++ AIRBUS ++Sogeti]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader (Members)** |
| --- | --- | --- | --- | --- |
| [M3 -> M7 -> M8] | D2.1.1 Report: Software Requirements - Evaluation of the natural language processing requirements set by the use cases | Doc. | Public | LORIA (KUL1) |
| [M6 -> M8] | D2.1.2 Data: Corpora (Text, Knowledge, Bi-Texts) and Report: Documentation of the corpora | Doc. | Public | LORIA (OBEO, AIRBUS, KUL1) |

### T2.2 - Hybrid approaches to semantic parsing [KUL1 + LORIA]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader (Members)** |
| --- | --- | --- | --- | --- |
| [M4 -> M6] | D2.2.1 Report: Overview and comparison of existing deep semantic parsers | Doc. | Public | KUL1 -> LORIA (KUL1) |

### T2.3 - Hybrid approaches to Natural Language Generation [LORIA + KUL2 + KUL1]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader (Members)** |
| --- | --- | --- | --- | --- |
| [M5 -> M7] | D2.3.1 Report: Overview and comparison of existing generators | Doc. | Public | LORIA (KUL1) |

### T2.4 - Definition of the target semantic representation language [+ KUL2 + KUL1 + LORIA ++ OBEO ++ AIRBUS]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M8 -> M10] | D2.5.1 Report: Specification of the Knowledge Representation Language(s) output by the parser and input to the generator | Doc. | Public | KUL2 -> LORIA (OBEO, AIRBUS) |



### T2.5 - Development of the semantic parser and of the generator [LORIA + KUL1 + MANTIS - KUL2 + AIRBUS ++ OBEO]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader (Members)** |
| --- | --- | --- | --- | --- |
| [M8 -> M10] | D2.5.2-1 Software: Semantic Parser and Report: Software Documentation (release 1) | SW | Public | KUL1 -> LORIA (KUL1, MANTIS) |
| [M20 -> M22] | D2.5.2-2 Software: Semantic Parser and Report: Software Documentation (release 2) | SW | Public | KUL1 -> LORIA (KUL1, MANTIS) |
| [M28 -> M30] | D2.5.2-3 Software: Semantic Parser and Report: Software Documentation (release 3) | SW | Public | KUL1 -> LORIA (KUL1, MANTIS) |

| **Month** | **Deliverable** | **Type** | **Access** | **Leader (Members)** |
| --- | --- | --- | --- | --- |
| [M8 -> M10] | D2.5.3-1 Software: Natural Language Generator and Report: Software Documentation (release 1) | SW | Public | LORIA (KUL1, MANTIS) |
| [M20 -> M22] | D2.5.3-2 Software: Natural Language Generator and Report: Software Documentation (release 2) | SW | Public | LORIA (KUL1, MANTIS) |
| [M28 -> M30] | D2.5.3-3 Software: Natural Language Generator and Report: Software Documentation (release 3) | SW | Public | LORIA (KUL1, MANTIS) |

| **Month** | **Deliverable** | **Type** | **Access** | **Leader (Members)** |
| --- | --- | --- | --- | --- |
| [M10 -> M12] | D2.5.4-1 Software: Integration in ModelWriter and Report: Software Documentation (release 1) | SW | Public | SA -> OBEO |
| [M22 -> M24] | D2.5.4-1 Software: Integration in ModelWriter and Report: Software Documentation (release 2) | SW | Public | SA -> OBEO |
| [M30 -> M32] | D2.5.4-1 Software: Integration in ModelWriter and Report: Software Documentation (release 3) | SW | Public | SA -> OBEO |

## WP3 - Model to/from Knowledge Base (UNIT)

### T3.1 - Review of M2M transformation approaches [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M3 -> M5] | D3.1.1 Review of model-to-model transformation approaches and technologies | Doc. | Public | UNIT |

### T3.2 - Specification and design of the M2M Transformation Framework [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M4 -> M6] | D3.2.1 M2M Transformation Framework architectural design document | Doc. | Public | UNIT |

### T3.3 - Development of the Transformation Manager component [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M5 -> M7] | D3.3.1 Transformation Manager architectural (TRAM) design document | Doc. | Public | UNIT |
| [M8 -> M10] | D3.3.2-1 Software: Transformation Manager component (release 1) | SW | Public | UNIT |
| [M20 -> M22] | D3.3.2-2 Software: Transformation Manager component (release 2) | SW | Public | UNIT |
| [M30 -> M32] | D3.3.2-3 Software: Transformation Manager component (release 3) | SW | Public | UNIT |

### T3.4 - Development of the Configuration Manager (COM) component [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M6 -> M8] | D3.4.1 Configuration Manager architectural design document | Doc. | Public | UNIT |
| [M8 -> M10] | D3.4.2-1 Software: Configuration Manager component (release 1) | SW | Public | UNIT |
| [M20 -> M22] | D3.4.2-2 Software: Configuration Manager component (release 2) | SW | Public | UNIT |
| [M30 -> M32] | D3.4.2-3 Software: Configuration Manager component (release 3) | SW | Public | UNIT |

### T3.5 - Development of the Traceability Manager component [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M7 -> M9] | D3.5.1 Traceability Manager architectural design document | Doc. | Public | UNIT |
| [M8 -> M10] | D3.5.2-1 Software: Traceability Manager component (release 1) | SW | Public | UNIT |
| [M20 -> M22] | D3.5.2-2 Software: Traceability Manager component (release 2) | SW | Public | UNIT |
| [M30 -> M32] | D3.5.2-3 Software: Traceability Manager component (release 3) | SW | Public | UNIT |

### T3.6 - Development of the Synchronization Manager component [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M8 -> M10] | D3.6.1 Synchronization Manager architectural design document | Doc. | Public | UNIT |
| [M8 -> M10] | D3.6.2-1 Software: Synchronization Manager component (release 1) | SW | Public | UNIT |
| [M20 -> M22] | D3.6.2-2 Software: Synchronization Manager component (release 2) | SW | Public | UNIT |
| [M30 -> M32] | D3.6.2-3 Software: Synchronization Manager component (release 3) | SW | Public | UNIT |

### T3.7 - Design of the model-to-model transformations [UNIT + MANTIS + KUL2]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M18 -> M10] | D3.7.1 Model-to-model transformations (from user-visible models to KB-stored models) design document | Doc. | Public | UNIT -> MANTIS |



### T3.8 - Implementation of the model-to-model transformations [UNIT + KUL2]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M11 -> M13] | D3.8.1-1 Software: Source and binary code of each model-to-model transformation (release 1) | SW | Public | UNIT |
| [M21 -> M23] | D3.8.1-3 Software: Source and binary code of each model-to-model transformation (release 2) | SW | Public | UNIT |
| [M31 -> M33] | D3.8.1-3 Software: Source and binary code of each model-to-model transformation (release 3) | SW | Public | UNIT |

### T3.9 - Validation of the M2M Transformation Framework [UNIT + MANTIS + KUL2 + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M32 -> M34] | D3.9.1 Test-plan for the M2M Transformation Framework | Doc. | Public | UNIT -> MANTIS |
| [M33 -> M35] | D3.9.2 Field experiment concerning ModelWriter model transformations | SW | Public | UNIT |

## WP4 - Knowledge Base Design and Implementation (Mantis)

### T4.1 - Design of the Knowledge Base [+ KUL2 - SA + OBEO + MANTIS + UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M6] -> [M7] | D4.1.1 Report: Knowledge Base Design document | Doc. | Public | KUL2 -> OBEO |

### T4.2 - API of the Knowledge Base [+ KUL2 + KOCSISTEM + OBEO + UNIT]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M6] | D4.2.1 Report: Interface Control Document (ICD) | Doc. | Public | KUL2 -> KOCSISTEM |

### T4.3 - Implementation of the Knowledge Base [- KUL2]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M11 -> M13] | D4.3.1-1 Software: Knowledge Base (release 1) | SW | Public | KUL2 -> MANTIS |
| [M19 -> M23] | D4.3.1-2 Software: Knowledge Base (release 2) | SW | Public | KUL2 -> MANTIS |
| [M31 -> M33] | D4.3.1-3 Software: Knowledge Base (release 3) | SW | Public | KUL2 -> MANTIS |

### T4.4 - Plug-in #1: ModelWriter-assisted requirements review [- KUL2 - SA]

This plug-in and associated deliverables were suggested by KUL2.

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M35] | D4.4.1 Report: Technical Note for ModelWriter-assisted Quality Review of Requirements | Doc. | Public | KUL2 -> ? |
| [M35] | D4.4.2 Software: Proof-of-concept model checker | SW | Public | KUL2 -> ? |

### T4.5 - Knowledge Base serialization and reuse plug-in [MANTIS]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M11 -> M13] | D4.5.1 Report: Technical Note for KB serialization and reuse | Doc. | Public | MANTIS |

### T4.6 - Plug-in #3: ModelWriter-assisted semantic comparison of 2 documents [OBEO + MANTIS]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M20] | D4.6.1 Report: Technical Note for ModelWriter-assisted Comparison of 2 Documents | Doc. | Public | OBEO |
| [M11 -> M13] | D4.6.2-1 Software: Proof-of-concept semantic comparison engine (release 1) | SW | Public | OBEO |
| [M19 -> M23] | D4.6.2-2 Software: Proof-of-concept semantic comparison engine (release 2) | SW | Public | OBEO |
| [M31 -> M33] | D4.6.2-3 Software: Proof-of-concept semantic comparison engine (release 3) | SW | Public | OBEO |



### T4.7 - Plug-in #2: ModelWriter-assisted compliance review [-SA]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D4.7.1 Report: Future ModelWriter-Enabled Use Cases | Doc. | Public | SA -> ? |

### T4.9 - Internal bi-directional synchronization mechanism [OBEO + UNIT]

### T4.10 - External synchronization mechanism for collaborating ModelWriters [SA]

## WP5 - Project Management (UNIT)

### T5.1 - Communication Management and Collaboration Infrastructure [UNIT + WP7 leader]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M1] | D5.1.1 Project Kick-Off Report and Project Management Plan | Doc. | Public | UNIT |



### T5.2 - Project Coordination and Reporting [UNIT - SA + Country Coordinators + WP Leaders]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M7] | D5.2.1 Project Progress Report (first half year) | Doc. | Confidential | UNIT |
| [M13] | D5.2.2 Project Progress Report (second half year) | Doc. | Confidential | UNIT |
| [M19] | D5.2.3 Project Progress Report (third half year) | Doc. | Confidential | UNIT |
| [M25] | D5.2.4 Project Progress Report (fourth half year) | Doc. | Confidential | UNIT |
| [M31] | D5.2.5 Project Progress Report (fifth half year) | Doc. | Confidential | UNIT |

### T5.3 - Closing Project [UNIT + WP Leaders]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M37] | D5.3.1 Final Project Report | Doc. | Confidential | UNIT |
| [M37] | D5.3.2 Updated State-of-the-art (Public Deliverable) | Doc. | Public | UNIT |

## WP6 - ModelWriter Architecture, Integration and Evaluation (OBEO)

### T6.1 - Experimental Prototyping [OBEO - SA + KUL2]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M5 -> M6] | D6.1.1 Software: Prototype Core ModelWriter (OBEO, SA, KUL2) | SW | Public | OBEO |

### T6.2 - Architectural Design [OBEO - SA + KUL2 + MANTIS + UNIT + technological WP Leaders]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M5 -> M6] | D6.2.1 Report: Architectural Design Document (ADD) (OBEO, SA, KUL2, Mantis) | Doc. | Public | OBEO |

### T6.3 - Writer Part enhancements [- SA]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D6.3.1-1 Software: Writer enhancements (release 1) | SW | Public | SA -> ? KoçSistem [Sogeti] |
| [M20] | D6.3.1-2 Software: Writer enhancements (release 2) | SW | Public | SA -> ? KoçSistem [Sogeti] |
| [M34] | D6.3.1-3 Software: Writer enhancements (release 3) | SW | Public | SA -> ? KoçSistem [Sogeti] |

### T6.4 - User Interfaces Implementation [- SA + OBEO]

User Interface for the Writer part [- SA]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M7] | D6.4.1 Report: Ergonomics Guidelines document for the Writer Part | Doc. | Public | SA -> UNIT [Sogeti] |
| [M10] | D6.4.2-1 Software: User Interface for the Writer part (release 1) | SW | Public | SA -> UNIT [Sogeti] |
| [M20] | D6.4.2-2 Software: User Interface for the Writer part (release 2) | SW | Public | SA -> UNIT [Sogeti] |
| [M34] | D6.4.2-3 Software: User Interface for the Writer part (release 3) | SW | Public | SA -> UNIT [Sogeti] |

Software: IDE-integrated User Interface to handle Synchronization [Obeo]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D6.4.3-1 Software: IDE-integrated User Interface to handle Synchronization issues major release (release 1) | SW | Public | OBEO |
| [M20] | D6.4.3-2 Software: IDE-integrated User Interface to handle Synchronization issues major release (release 2) | SW | Public | OBEO |
| [M34] | D6.4.3-3 Software: IDE-integrated User Interface to handle Synchronization issues major release (release 3) | SW | Public | OBEO |

### T6.5 - Acceptance Test Plan [- SA + UNIT + KS + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D6.5.1-1 Report: Acceptance Test Plan (release 1) (SA + all) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M20] | D6.5.1-2 Report: Acceptance Test Plan (release 2) (SA + all) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M34] | D6.5.1-3 Report: Acceptance Test Plan (release 3) (SA + all) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M10] | D6.5.2-1 Software: Automated Acceptance Tests (release 1) (SA + all | SW | Public | SA -> ? KoçSistem [Sogeti] |
| [M20] | D6.5.2-2 Software: Automated Acceptance Tests (release 2) (SA + all) | SW | Public | SA -> ? KoçSistem [Sogeti] |
| [M34] | D6.5.2-3 Software: Automated Acceptance Tests (release 3) (SA + all) | SW | Public | SA -> ? KoçSistem [Sogeti] |

### T6.6 - Acceptance Test Procedures [- SA + UNIT + KS + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D6.6.1-1 Report: Acceptance Test Procedures (release 1) (SA + all) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M20] | D6.6.1-2 Report: Acceptance Test Procedures (release 2) (SA + all) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M34] | D6.6.1-3 Report: Acceptance Test Procedures (release 3) (SA + all) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |



### T6.7 - ModelWriter Integration [OBEO + UNIT + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M11] | D6.7.1-1 Software: ModelWriter major release (release 1) | SW | Public | OBEO |
| [M23] | D6.7.1-2 Software: ModelWriter major release (release 2) | SW | Public | OBEO |
| [M35] | D6.7.1-3 Software: ModelWriter major release (release 3) | SW | Public | OBEO |

### T6.8 - Cyclic Evaluation of Analysis Performance [- SA + OBEO + LORIA + UNIT + KS + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M12] | D6.8.1-1 Report: Evaluation report (release 1) (All) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M24] | D6.8.1-2 Report: Evaluation report (release 2) (All) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |
| [M36] | D6.8.1-3 Report: Evaluation report (release 3) (All) | Doc. | Public | SA -> ? KoçSistem [Sogeti] |

## WP7 - Dissemination and Exploitation (OBEO)

### T7.1 - Dissemination Plan [OBEO + UNIT + SA + LORIA + KS + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M4 -> M6] | D7.1.1 Dissemination Plan | Doc. | Public | OBEO |

### T7.2 - Business Model & Exploitation Plan [AIRBUS + SA + OBEO + all industrial partners]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M7] | D7.2.1-1 Exploitation Plan (release 1) | Doc. | Public | AIRBUS ->? |
| [M22] | D7.2.1-2 Exploitation Plan (release 2) | Doc. | Public | AIRBUS ->? |
| [M34] | D7.2.1-3 Exploitation Plan (release 3) | Doc. | Public | AIRBUS ->? |
| [M7] | D7.2.2 Marketing Plan | Doc. | Public | AIRBUS |
| [M34] | D7.2.3 Road-map for future exploitation and pre-competition survey | Doc. | Public | AIRBUS |

### T7.3 - Workshops & Events [+ KUL2 + UNIT + OBEO + KS + AIRBUS + ALL]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M31] | D7.3.1 Newsletter - International Conference Announcement | Doc. | Public | KUL2 -> UNIT |

### T7.4 - ModelWriter-ITEA Consortium Website [- SA]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M1 -> M8] | D7.4.1 ModelWriter-ITEA website including secured intranet | SW | Public | SA -> OBEO -> ? KoçSistem |

### T7.5 - Community Forum & Open Source Campaign [+ KUL2 + OBEO]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D7.5.1 Technical-oriented talk about the principles and benefits of the ModelWriter-ITEA approach and tooling | Doc. | Public | KUL2 -> OBEO |
| [M10] | D7.5.2 Research-oriented talk about the principles and benefits of the ModelWriter-ITEA approach and tooling | Doc. | Public | KUL2 -> UNIT |

### T7.6 - Social Networks [UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M10] | D7.6.1 ModelWriter-ITEA's Facebook Group | SW | Public | UNIT |
| [M10] | D7.6.2 ModelWriter-ITEA's LinkedIn Group | SW | Public | UNIT |
| [M10] | D7.6.3 ModelWriter-ITEA's Twitter Group | SW | Public | UNIT |
| [M10] | D7.6.4 ModelWriter-ITEA's Google+ Group | SW | Public | UNIT |

### T7.7 - Standardization [LORIA + UNIT + KOCSISTEM]

| **Month** | **Deliverable** | **Type** | **Access** | **Leader** |
| --- | --- | --- | --- | --- |
| [M34] | D7.7.1 ModelWriter and standardization activities | SW | Public | LORIA |